## Sheet1
TravelMe | [5 empty] | When changing things, right click on the y axis and format it. | Change the Max and Min to the range table values. | To create more tasks, click on the graph and drag the highlighted fields to the desired number.
Tasks | Start Date | Duration(Days) | End Date | Range for Gantt Chart
Define Requirements, User Stories, Database Objects | 2015-08-17 | 7 | 2015-08-24 | Axis Values
Design & Implement Database / Normalise | 2015-08-24 | 3 | 2015-08-27 | Start Date | 42233
Develop Repository Layer | 2015-08-27 | 5 | 2015-09-01 | End Date | 42300
Develop nHibernate Mappings | 2015-09-01 | 5 | 2015-09-06
Develop Service Layer | 2015-09-06 | 7 | 2015-09-13
Develop Controllers | 2015-09-13 | 5 | 2015-09-18
Develop Views | 2015-09-18 | 7 | 2015-09-25
Site CSS Design | 2015-09-25 | 14 | 2015-10-09
Site JavaScript Design | 2015-10-09 | 14 | 2015-10-23
Formulas:
End Date = [Start Date]+[Duration(Days)]
Start Date = [End Date, row above]